## Sheet1
Risk Register For Tourism and Travel Management Date: April 21, 2023
Project Name: Tourism and Travel Management
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
556128 | 1 | Hotel overbooking | hotel overbooking occurs when a hotel accepts more reservations than the number of available rooms. | Operational | unexpected cancellations, system errors, or miscommunications | Technical errors, seasonal demand,flight cancellation or delay | Work with hotel to find alternative accommodations for affected guests | Project Manager | High | High | Open
556129 | 2 | Weathedisruption | Weather disruption risk is the potential threat of adverse weather conditions impacting a project or an organization's operations. | Environmental | Schedule delays, safety hazards, property damage,revenue loss | Hurricanes,snowstorms,heatwaves,wildfires,floods | Risk Acceptance. | Operations Team | Medium | Medium | Open
556130 | 3 | Vendor bankruptcy | Vendor bankruptcy risk is the potential threat of a vendor or supplier going bankrupt and being unable to fulfill its contractual obligations to its customers. | Financial | cause interruptions in the supply chain, leading to increased costs and operational disruptions | Financial instability,Operational issues,Legal issues | Risk Acceptance. | Finance team | Low | High | Open
556131 | 4 | Transportation delays | Transportation delay risk is the potential threat of delays or interruptions in the movement of goods or people due to issues in transportation networks. | Operational | natural disasters, accidents, strikes, or technical failures | accidents,congestion,security issues,labour strikes | Risk Mitigation. | Operations Team | High | Medium | Open
556132 | 5 | Natural disasters | Natural disasters, such as hurricanes, earthquakes, or floods, can disrupt transportation networks and lead to delays in the movement of goods and people. | Environmental | Existing applications that are similar. | Applications. | Risk Acceptance. | Risk Management team | Low | High | Open
556133 | 6 | Changes in government regulations | Changes in government regulation risk is the potential threat of new or changing laws, regulations, or policies that could impact an organization's operations, financial position, or reputation | People Risk. | political leadership, economic conditions, or societal attitudes. | Compliance costs,Business disruption,Legal liabilities or Reputation damage | Risk Mitigation. | Project Manager | High | High | Closed